## weekly Report
Decentralized Capital Budget Programme - 2021
Division wise Physical and Financial Weekly Progress as of 2021.08.02
Division:-
No. | GN Division | Name of the Project | Projects | [12 empty] | Allocation | [12 empty] | ** Physical Progress (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  |  | No. of Projects Approved |  |  | Total categorized by Sectors * | [9 empty] | Allocation Made (Rs.) |  |  | Total Allocation Categorized by Sectors * | [9 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | Construction | Goods / Services Purchase | Total | WS | EL | RA | RE | MI | CD | VL | CP | OI | FE | Construction | Goods / Services Purchase | Total | WS | EL | RA | RE | MI | CD | VL | CP | OI | FE |  | Estimates Approved & Bid Documents Prepared (B 1) | Quotation / Bid called (B 2) | Quotation / Bid Received (B 3) | Contract Awarded (B 4)
1 | Samagipura | Construction of culvert near Mr. Sirisena's house | 1 | [12 empty] | 425000 |  | 425000 |  |  | 425000 | [8 empty] | 1 | [9 empty] | 600 | bar: Total; Total categorized by Sectors * RA
2 | Habarugala | Extension of Pipeline 300, Jayashakthi Mawatha, By Road Water Pipeline. | 1 | [12 empty] | 200000 |  | 200000 | 200000 | [9 empty] | 1 | [10 empty] | 40 | bar: Total to Total categorized by Sectors * WS
3 | Habarugala | Sevanagala Samadhipura Mahagama Colony No. 149/2 HM Providing electricity facilities for the house of Mrs. Dhammika Priyadarshini Hewamulla | 1 | [12 empty] | 20000 |  | 20000 |  | 20000 | [14 empty] | 1 |  |  |  |  | 5 | bar: Total; Total categorized by Sectors * EL
4 | Katupilagama | Providing a buffet set to the Rohana Farmers' Association. |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 130 | bar: Total; Total categorized by Sectors * FE
5 | Muthuminigama | Donating a buffet set to Suhada Govi ​​Sanwidhanaya |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 106 | bar: Total; Total categorized by Sectors * FE
6 | Nugegalayaya | Donating a buffet set to Tunkamayaya Rural Development Society |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 143 | bar: Total; Total categorized by Sectors * FE
7 | Habarugala | Donating a buffet set to the Parakum Farmers' Association. |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 128 | bar: Total; Total categorized by Sectors * FE
8 | Kiriwawe | Donating a buffet set to Samagi Rural Development Society |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 152 | bar: Total; Total categorized by Sectors * FE
9 | Sevanagala | Donating a buffet set to Laksiri Welfare Society |  | 1 | [12 empty] | 58000 | 58000 | [9 empty] | 58000 | [5 empty] | 1 | [5 empty] | 150 | bar: Total; Total categorized by Sectors * FE
10 | Habarugala | Providing equipment for Bodhiraja Pre-School |  | 1 | [12 empty] | 20000 | 20000 | [9 empty] | 20000 | [5 empty] | 1 | [5 empty] | 25 | bar: Total; Total categorized by Sectors * FE
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
District Total |  |  | 3 | 7 | 10 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 645000 | 368000 | 1013000 | 200000 | 20000 | 425000 | 0 | 0 | 0 | 0 | 0 | 0 | 368000 | 1 | 1 | 0 | 0 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 1479
|  | * Projects should be categorized for following sectors |  |  | Total categorized by Sectors * CD: ** Physical progress
|  | Sector Name |  |  | Total: Circular code
|  | WS- Rural Water Supply |  |  | Total: 1.1; Total categorized by Sectors * CD: A - Estimates are being / to be prepared
|  | EL- Rural Electricity |  |  | Total: 1.2; Total categorized by Sectors * CD: B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received , B-4= Contract Awarded
|  | RA-Rural Access |  |  | Total: 1.3; Total categorized by Sectors * CD: Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
|  | RE- Rural Economy |  |  | Total: 1.4; Total categorized by Sectors * CD: C - For Constructions : Start construction work ,40% completed, Other : placed order for goods
|  | MI- Minor Irrigation |  |  | Total: 1.7; Total categorized by Sectors * CD: D - For Constructions : 60% completed Other : Received goods /instruments as per the order
|  | CD- Community Development |  |  | Total: 1.6; Total categorized by Sectors * CD: E - For Constructions 80% completed Other : Received goods /instruments as per the order
|  | VL- Vocational and Livelihood |  |  | Total: 1.11; Total categorized by Sectors * CD: F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
|  | CP- Community Protection |  |  | Total: 1.1; Total categorized by Sectors * CD: G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
|  | OI- Other Infrastructure |  |  | Total: 1.12
|  | FE- Supply of facilities and Equipment |  |  | Total: 1.5 , 1.8 , 1.9